## Sheet1
S No | Name of the Task | Responsibility | Start Date | End Date | Status | Comments/Remarks (if any)
1 | Deployment on test server (Oracle Linux Server) | DVS
2 | Database schema and the required tables created | DVS
3 | OCR for text extraction and Libre office deployed for preview | DVS
4 | Initial requirement for creating the schema classification | DVS
5 | Data analysis in progress so as to map the data between vicidocs and ERDMS | DVS
6 | First presentation of application to Business | DVS
7 | Extraction of classification Schema | DVS | 2022-09-05 | 2022-09-06 | Open
8 | Loading first test of Classification Schema | DVS | 2022-09-06 | 2022-09-08 | Open
9 | Analysis of meta data | DVS | 2022-09-08 | 2022-09-10 | Open
10 | Analysis of users, roles and configuration in current application | DVS | 2022-09-06 | 2022-09-10 | Open
11 | Analysis of document types | DVS | 2022-09-06 | 2022-09-13 | Open
11 | Further Requirements discussion | DVS & ZRA | 2022-09-09 | 2022-09-09 | Open
Challenges: Current base has an old structural set-up without many relations between the tables thereby making the analysis slow Understanding the requirements and some other data specific questions. Requirements from ZRA: Production server for deploying the solution Extraction of data from existing database for migration process.